## Sheet1
| 3/7/2021 - 3/11/2021 | 3/12/2021 - 3/18/2021 | 3/19/2021 - 3/25/2021 |  | 3/26/2021 - 4/1/2021 | 4/2/2021 - 4/8/2021 | 4/9/2021 - 4/15/2021 |  | 4/16/2021 - 4/22/2021 | 4/23/2021 - 4/29/2021
Project due dates: | Collect and preprocess the data | Construct the model fully (Using python functions) | Validate the model (Using statistics) | Milestone 3: Progress Report 1 ( 3/26/2021) |  |  |  | Milestone 4: Progress Report 2 (4/16/2021) |  |  | Milestone 5: Final Report
Homework due dates: |  | HW 2: Sentiment Analysis with Sequential Models (3/13/2021) |  |  |  | HW 3: Generative Models with VAEs (4/3/2021)
Responsibilities: | Collect and preprocess the data (Izzat) | Construct the model fully (Using python functions) (Max and Izzat) | Validate the model (Using statistics) (Izzat and Ryan) | Timestamps | 1 | 2 | 3 | 4 | 5 | 6
Outline | Collect and buy data from report list | 3 inputs variables/layers | Run (Anova) RCBD on the test data for each country using R | real GDP growth (Malaysia) | 21323 | 42323 | 124 | 312312 | 1213 | 124124
| Import population of the data from the countries chosen | 2 merging variables (concatenate) | Put in the report analysis in Latex | real GDP growth (US) | 21323 | 42323 | 124 | 312312 | 1213 | 124124
| Separate the data into training data (Everything until the last three time stamps) and testing data (Last three time stamps) | 2 model functions | Put in the report analysis in Latex | real GDP growth (Japan) | 21323 | 42323 | 124 | 312312 | 1213 | 124124
|  | Train on each country from everything until the last three time stamps for each country. | Document reasoning for doing RCBD (Single/Multi Anova) | real GDP growth (UK) | 21323 | 42323 | 124 | 312312 | 1213 | 124124
|  | Test on each country on the last three time stamps | Write report
|  | Export the test data results into excel sheet (CSV File) for statistical analysis |  | Randomized Complete Block Design (Done by R code) | We block by countries (It can account for variances between blocks) | Treatment: Long run parameter multi anove: Multiple parameters |  | Average the accuracy of the last three stamps
|  | Deadline: 3/22/2021 | Deadline: 3/26/2022 |  | Run F-test
Homework 2 Requirements: | Design and implement at least two sequential architectures for this problem. | Meet Dr. Stephen Scott or Eleanor Quint to ask any questions | Responsibilities:
| For each architecture you should use an attention mechanism and a regularizer, and try at least two settings of hyperparameter values | Questions from Izzat: 1) How to implement attention mechanism for model.fit sequential form? | Introduction and problem description Done Friday and Saturday | Ryan | Please Note:
| Thus you will evaluate at least four models |  | Design and implement at least two sequential architectures for this problem.For each architecture you should use an attention mechanism and a regularizer, and try at least two settings of hyperparameter values. 40 epochs. Get done by Friday | 2 models from Max (Feel free to be creative and make your own models. Just make sure the model can take inputs as expected) | Training/Validation data uses k-fold cross-validation. This is put into the models. So we need to get the input shapes and types for the models to be correct first, then we can use k-fold cross-validation | Please document all code and put them straight into similar templates as the previous homework.
| You should use k-fold cross-validation for this process |  |  | 2 models from Izzat (I will do models similar to our project so we can cut short the time for creating models and just concatenate where needed)
| You should then describe your experimental results, including confusion matrices and basic confidence intervals on the probability of generalization error, and draw conclusions from your results (conclusions must be justified by your presented results). |  | You should use k-fold cross-validation for this process. Get this done asap | Implemented by Ryan
|  |  | You should then describe your experimental results, including confusion matrices and basic confidence intervals on the probability of generalization error, and draw conclusions from your results (conclusions must be justified by your presented results). Done Friday night and Saturday | Izzat and Max (Ryan can help explain further the confusion matrices and the basic confidence intervals on the probability of generalization error)
|  |  | Conclusion Done Saturday | Izzat and Max and Ryan